## Sheet1
Siromni TASK LIST
TASK NAME | Dev Status | Milestone | DURATION | Budget | Client status on Task | STATUS
Mini Browser |  | 2ST | 5 days |  |  | Not started
Create project under the pipeline |  | 2ST | 7 days |  |  | Not started
create new module for update terms and conditions and princy and police |  | 1St | 2 days |  |  | Done
check invite working properly |  | 1St | 0 |  |  | Done
add payment menu in backoffice |  | 1St | 0 |  |  | Done
inbox working for all type of users |  | 1St | 0 |  |  | Done
process issue in interview question |  | 1St | 1 day |  |  | Not started
update task button |  | 2ST | 2 day | 180 |  | Not started
pipeline not delete from the dashboard |  | 1St | 2 hour |  |  | Not started
issue from send msg from the dashboard image only issue |  | 1St | 2 hour |  |  | Not started
message not showing on the dashboard(M-2) |  | 2ST | 3-4 hours | 54 |  | Not started
appointments not showing on the dashboard show datetime as well(M-2) |  | 2ST | 3 hours | 54 |  | Not started
show a popup msg before delete the task(create a trash bin) M-2 |  | 2ST | 1 day for everwhere | 90 |  | Not started
create new circle for each 7 person(M-2) |  | 2ST | 2 days | 180 |  | Not started
show full datetime under the notes |  | 1St | 1 hour |  |  | Not started
check validation for the contacts (M-2) |  | 2ST | 1 day | 90 |  | Not started
show number in contact on the dashboard like the above (M-2) |  | 2ST | 2 hours | 36 |  | Not started
need to rename this button (feedback and suggestion) |  | 1St | 1 hour |  |  | Not started
add a contact us button and the other pages links on the menu (M-2) |  | 2ST | 5-6 hours | 60 |  | Not started
check filter for events |  | 1St | 5-6 hours |  |  | Not started
space between time and am |  | 1St | 1 hour |  |  | Not started
create new module for invite event and show invitation to the other user(M-2) |  | 2ST | 3 days | 270 |  | Not started
change delete icon to X |  | 1St | 1 hour |  |  | Not started
image show own image |  | 1St | 1 hour |  |  | Not started
show last used apps to the usrs(M-2)(currently hide the placeholder ) |  | 2ST | 2 days | 180 |  | Not started
upload button not working |  | 2ST | 5 hours | 60 |  | Not started
create a new module for the notification for the project update(M-2) |  | 2ST | 3 days | 270 |  | Not started
create module for instant message (M-2) |  | 2ST | 3 days | 270 |  | Not started
redirect the user to the subscription page before clicking on the signup |  | 1St | 1 hour |  |  | Not started
fix the same issue for the office crm also (M-1-M-2) |  | 2ST | none |  |  | Not started